## Post tensioning
Post tensioning — calé sur les coulées du solveur
Départ : 2 jours après le démarrage de la coulée de l'élément suivant sur la même ligne (règle Dywidag). Durées en postes — Threading 6, Stressing 4, Grouting 2 : paramètres à confirmer.
Scénario : reel.xlsm, date de référence 2026-08-05, 9 élément(s) en retard, 0 bloqué(s), fin de production 2029-11-02
26/09/2026 → 27/11/2026 · page 1 / 18
|  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [8 empty] | 61
|  | Stressing | [14 empty] | 61
|  | Grouting | [18 empty] | 61
| PL-2 | Threading | [10 empty] | 62
|  | Stressing | [16 empty] | 62
|  | Grouting | [20 empty] | 62
Basin B | PL-3 | Threading | [12 empty] | 63
|  | Stressing | [18 empty] | 63
|  | Grouting | [22 empty] | 63
| PL-4 | Threading | 64
|  | Stressing | [6 empty] | 64
|  | Grouting | [10 empty] | 64
Basin C | PL-5 | Threading |  |  | 67
|  | Stressing | [8 empty] | 67
|  | Grouting | [12 empty] | 67
| SPE | Threading
Stressing
Grouting
28/11/2026 → 29/01/2027 · page 2 / 18
|  |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
Stressing
Grouting
| PL-2 | Threading
Stressing
Grouting
Basin B | PL-3 | Threading
Stressing
Grouting
| PL-4 | Threading
Stressing
Grouting
Basin C | PL-5 | Threading
Stressing
Grouting
| SPE | Threading
Stressing
Grouting
30/01/2027 → 02/04/2027 · page 3 / 18
|  |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [36 empty] | 04
|  | Stressing | [42 empty] | 04
|  | Grouting | [46 empty] | 04
| PL-2 | Threading | [38 empty] | 58
|  | Stressing | [44 empty] | 58
|  | Grouting | [48 empty] | 58
Basin B | PL-3 | Threading | [40 empty] | 60
|  | Stressing | [46 empty] | 60
|  | Grouting | [50 empty] | 60
| PL-4 | Threading | [28 empty] | 59
|  | Stressing | [34 empty] | 59
|  | Grouting | [38 empty] | 59
Basin C | PL-5 | Threading | [30 empty] | 03
|  | Stressing | [36 empty] | 03
|  | Grouting | [40 empty] | 03
| SPE | Threading
Stressing
Grouting
03/04/2027 → 04/06/2027 · page 4 / 18
|  |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [78 empty] | 56
|  | Stressing | [84 empty] | 56
|  | Grouting | [88 empty] | 56
| PL-2 | Threading | [80 empty] | 07
|  | Stressing | [86 empty] | 07
|  | Grouting | [90 empty] | 07
Basin B | PL-3 | Threading | [124 empty] | 05
Stressing
Grouting
| PL-4 | Threading
Stressing
Grouting
Basin C | PL-5 | Threading
Stressing
Grouting
| SPE | Threading
Stressing
Grouting
05/06/2027 → 06/08/2027 · page 5 / 18
|  |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [92 empty] | 09
|  | Stressing | [98 empty] | 09
|  | Grouting | [102 empty] | 09
| PL-2 | Threading | [94 empty] | 10
|  | Stressing | [100 empty] | 10
|  | Grouting | [104 empty] | 10
Basin B | PL-3 | Threading
|  | Stressing |  |  |  |  | 05
|  | Grouting | [8 empty] | 05
| PL-4 | Threading | 57
|  | Stressing | [6 empty] | 57
|  | Grouting | [10 empty] | 57
Basin C | PL-5 | Threading | [58 empty] | 06
|  | Stressing | [64 empty] | 06
|  | Grouting | [68 empty] | 06
| SPE | Threading
Stressing
Grouting
07/08/2027 → 08/10/2027 · page 6 / 18
|  |  | 316 |  | 317 |  | 318 |  | 319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [106 empty] | 50
|  | Stressing | [112 empty] | 50
|  | Grouting | [116 empty] | 50
| PL-2 | Threading | [108 empty] | 49
|  | Stressing | [114 empty] | 49
|  | Grouting | [118 empty] | 49
Basin B | PL-3 | Threading | [12 empty] | 55
|  | Stressing | [18 empty] | 55
|  | Grouting | [22 empty] | 55
| PL-4 | Threading | [14 empty] | 08
|  | Stressing | [20 empty] | 08
|  | Grouting | [24 empty] | 08
Basin C | PL-5 | Threading | [72 empty] | 54
|  | Stressing | [78 empty] | 54
|  | Grouting | [82 empty] | 54
| SPE | Threading
Stressing
Grouting
09/10/2027 → 10/12/2027 · page 7 / 18
|  |  | 379 |  | 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399 |  | 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420 |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430 |  | 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440 |  | 441
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [120 empty] | 45
Stressing
Grouting
| PL-2 | Threading | [122 empty] | 44
Stressing
Grouting
Basin B | PL-3 | Threading | [26 empty] | 53
|  | Stressing | [32 empty] | 53
|  | Grouting | [36 empty] | 53
| PL-4 | Threading | [28 empty] | 52
|  | Stressing | [34 empty] | 52
|  | Grouting | [38 empty] | 52
Basin C | PL-5 | Threading | [86 empty] | 51
|  | Stressing | [92 empty] | 51
|  | Grouting | [96 empty] | 51
| SPE | Threading
Stressing
Grouting
11/12/2027 → 11/02/2028 · page 8 / 18
|  |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460 |  | 461 |  | 462 |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480 |  | 481 |  | 482 |  | 483 |  | 484 |  | 485 |  | 486 |  | 487 |  | 488 |  | 489 |  | 490 |  | 491 |  | 492 |  | 493 |  | 494 |  | 495 |  | 496 |  | 497 |  | 498 |  | 499 |  | 500 |  | 501 |  | 502 |  | 503 |  | 504
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
|  | Stressing | 45
|  | Grouting |  |  |  |  | 45
| PL-2 | Threading
|  | Stressing |  |  | 44
|  | Grouting | [6 empty] | 44
Basin B | PL-3 | Threading
Stressing
Grouting
| PL-4 | Threading
Stressing
Grouting
Basin C | PL-5 | Threading
Stressing
Grouting
| SPE | Threading
Stressing
Grouting
12/02/2028 → 14/04/2028 · page 9 / 18
|  |  | 505 |  | 506 |  | 507 |  | 508 |  | 509 |  | 510 |  | 511 |  | 512 |  | 513 |  | 514 |  | 515 |  | 516 |  | 517 |  | 518 |  | 519 |  | 520 |  | 521 |  | 522 |  | 523 |  | 524 |  | 525 |  | 526 |  | 527 |  | 528 |  | 529 |  | 530 |  | 531 |  | 532 |  | 533 |  | 534 |  | 535 |  | 536 |  | 537 |  | 538 |  | 539 |  | 540 |  | 541 |  | 542 |  | 543 |  | 544 |  | 545 |  | 546 |  | 547 |  | 548 |  | 549 |  | 550 |  | 551 |  | 552 |  | 553 |  | 554 |  | 555 |  | 556 |  | 557 |  | 558 |  | 559 |  | 560 |  | 561 |  | 562 |  | 563 |  | 564 |  | 565 |  | 566 |  | 567
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [36 empty] | 42
|  | Stressing | [42 empty] | 42
|  | Grouting | [46 empty] | 42
| PL-2 | Threading | [38 empty] | 13
|  | Stressing | [44 empty] | 13
|  | Grouting | [48 empty] | 13
Basin B | PL-3 | Threading | [82 empty] | 48
|  | Stressing | [88 empty] | 48
|  | Grouting | [92 empty] | 48
| PL-4 | Threading | [84 empty] | 47
|  | Stressing | [90 empty] | 47
|  | Grouting | [94 empty] | 47
Basin C | PL-5 | Threading
Stressing
Grouting
| SPE | Threading
Stressing
Grouting
15/04/2028 → 16/06/2028 · page 10 / 18
|  |  | 568 |  | 569 |  | 570 |  | 571 |  | 572 |  | 573 |  | 574 |  | 575 |  | 576 |  | 577 |  | 578 |  | 579 |  | 580 |  | 581 |  | 582 |  | 583 |  | 584 |  | 585 |  | 586 |  | 587 |  | 588 |  | 589 |  | 590 |  | 591 |  | 592 |  | 593 |  | 594 |  | 595 |  | 596 |  | 597 |  | 598 |  | 599 |  | 600 |  | 601 |  | 602 |  | 603 |  | 604 |  | 605 |  | 606 |  | 607 |  | 608 |  | 609 |  | 610 |  | 611 |  | 612 |  | 613 |  | 614 |  | 615 |  | 616 |  | 617 |  | 618 |  | 619 |  | 620 |  | 621 |  | 622 |  | 623 |  | 624 |  | 625 |  | 626 |  | 627 |  | 628 |  | 629 |  | 630
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [64 empty] | 15
|  | Stressing | [70 empty] | 15
|  | Grouting | [74 empty] | 15
| PL-2 | Threading | [66 empty] | 39
|  | Stressing | [72 empty] | 39
|  | Grouting | [76 empty] | 39
Basin B | PL-3 | Threading | [110 empty] | 43
|  | Stressing | [116 empty] | 43
|  | Grouting | [120 empty] | 43
| PL-4 | Threading | [112 empty] | 11
|  | Stressing | [118 empty] | 11
|  | Grouting | [122 empty] | 11
Basin C | PL-5 | Threading | [16 empty] | 46
|  | Stressing | [22 empty] | 46
|  | Grouting | [26 empty] | 46
| SPE | Threading
Stressing
Grouting
17/06/2028 → 18/08/2028 · page 11 / 18
|  |  | 631 |  | 632 |  | 633 |  | 634 |  | 635 |  | 636 |  | 637 |  | 638 |  | 639 |  | 640 |  | 641 |  | 642 |  | 643 |  | 644 |  | 645 |  | 646 |  | 647 |  | 648 |  | 649 |  | 650 |  | 651 |  | 652 |  | 653 |  | 654 |  | 655 |  | 656 |  | 657 |  | 658 |  | 659 |  | 660 |  | 661 |  | 662 |  | 663 |  | 664 |  | 665 |  | 666 |  | 667 |  | 668 |  | 669 |  | 670 |  | 671 |  | 672 |  | 673 |  | 674 |  | 675 |  | 676 |  | 677 |  | 678 |  | 679 |  | 680 |  | 681 |  | 682 |  | 683 |  | 684 |  | 685 |  | 686 |  | 687 |  | 688 |  | 689 |  | 690 |  | 691 |  | 692 |  | 693
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [78 empty] | 37
|  | Stressing | [84 empty] | 37
|  | Grouting | [88 empty] | 37
| PL-2 | Threading | [80 empty] | 18
|  | Stressing | [86 empty] | 18
|  | Grouting | [90 empty] | 18
Basin B | PL-3 | Threading | [124 empty] | 41
Stressing
Grouting
| PL-4 | Threading
Stressing
Grouting
Basin C | PL-5 | Threading | [44 empty] | 12
|  | Stressing | [50 empty] | 12
|  | Grouting | [54 empty] | 12
| SPE | Threading
Stressing
Grouting
19/08/2028 → 20/10/2028 · page 12 / 18
|  |  | 694 |  | 695 |  | 696 |  | 697 |  | 698 |  | 699 |  | 700 |  | 701 |  | 702 |  | 703 |  | 704 |  | 705 |  | 706 |  | 707 |  | 708 |  | 709 |  | 710 |  | 711 |  | 712 |  | 713 |  | 714 |  | 715 |  | 716 |  | 717 |  | 718 |  | 719 |  | 720 |  | 721 |  | 722 |  | 723 |  | 724 |  | 725 |  | 726 |  | 727 |  | 728 |  | 729 |  | 730 |  | 731 |  | 732 |  | 733 |  | 734 |  | 735 |  | 736 |  | 737 |  | 738 |  | 739 |  | 740 |  | 741 |  | 742 |  | 743 |  | 744 |  | 745 |  | 746 |  | 747 |  | 748 |  | 749 |  | 750 |  | 751 |  | 752 |  | 753 |  | 754 |  | 755 |  | 756
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [92 empty] | 19
|  | Stressing | [98 empty] | 19
|  | Grouting | [102 empty] | 19
| PL-2 | Threading | [94 empty] | 20
|  | Stressing | [100 empty] | 20
|  | Grouting | [104 empty] | 20
Basin B | PL-3 | Threading
|  | Stressing |  |  |  |  | 41
|  | Grouting | [8 empty] | 41
| PL-4 | Threading | 14
|  | Stressing | [6 empty] | 14
|  | Grouting | [10 empty] | 14
Basin C | PL-5 | Threading | [58 empty] | 40
|  | Stressing | [64 empty] | 40
|  | Grouting | [68 empty] | 40
| SPE | Threading
Stressing
Grouting
21/10/2028 → 22/12/2028 · page 13 / 18
|  |  | 757 |  | 758 |  | 759 |  | 760 |  | 761 |  | 762 |  | 763 |  | 764 |  | 765 |  | 766 |  | 767 |  | 768 |  | 769 |  | 770 |  | 771 |  | 772 |  | 773 |  | 774 |  | 775 |  | 776 |  | 777 |  | 778 |  | 779 |  | 780 |  | 781 |  | 782 |  | 783 |  | 784 |  | 785 |  | 786 |  | 787 |  | 788 |  | 789 |  | 790 |  | 791 |  | 792 |  | 793 |  | 794 |  | 795 |  | 796 |  | 797 |  | 798 |  | 799 |  | 800 |  | 801 |  | 802 |  | 803 |  | 804 |  | 805 |  | 806 |  | 807 |  | 808 |  | 809 |  | 810 |  | 811 |  | 812 |  | 813 |  | 814 |  | 815 |  | 816 |  | 817 |  | 818 |  | 819
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [106 empty] | 24
|  | Stressing | [112 empty] | 24
|  | Grouting | [116 empty] | 24
| PL-2 | Threading | [108 empty] | 25
|  | Stressing | [114 empty] | 25
|  | Grouting | [118 empty] | 25
Basin B | PL-3 | Threading | [12 empty] | 16
|  | Stressing | [18 empty] | 16
|  | Grouting | [22 empty] | 16
| PL-4 | Threading | [14 empty] | 38
|  | Stressing | [20 empty] | 38
|  | Grouting | [24 empty] | 38
Basin C | PL-5 | Threading | [72 empty] | 17
|  | Stressing | [78 empty] | 17
|  | Grouting | [82 empty] | 17
| SPE | Threading
Stressing
Grouting
23/12/2028 → 23/02/2029 · page 14 / 18
|  |  | 820 |  | 821 |  | 822 |  | 823 |  | 824 |  | 825 |  | 826 |  | 827 |  | 828 |  | 829 |  | 830 |  | 831 |  | 832 |  | 833 |  | 834 |  | 835 |  | 836 |  | 837 |  | 838 |  | 839 |  | 840 |  | 841 |  | 842 |  | 843 |  | 844 |  | 845 |  | 846 |  | 847 |  | 848 |  | 849 |  | 850 |  | 851 |  | 852 |  | 853 |  | 854 |  | 855 |  | 856 |  | 857 |  | 858 |  | 859 |  | 860 |  | 861 |  | 862 |  | 863 |  | 864 |  | 865 |  | 866 |  | 867 |  | 868 |  | 869 |  | 870 |  | 871 |  | 872 |  | 873 |  | 874 |  | 875 |  | 876 |  | 877 |  | 878 |  | 879 |  | 880 |  | 881 |  | 882
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
Stressing
Grouting
| PL-2 | Threading
Stressing
Grouting
Basin B | PL-3 | Threading | [54 empty] | 36
|  | Stressing | [60 empty] | 36
|  | Grouting | [64 empty] | 36
| PL-4 | Threading | [56 empty] | 35
|  | Stressing | [62 empty] | 35
|  | Grouting | [66 empty] | 35
Basin C | PL-5 | Threading | [114 empty] | 34
|  | Stressing | [120 empty] | 34
|  | Grouting | [124 empty] | 34
| SPE | Threading
Stressing
Grouting
24/02/2029 → 27/04/2029 · page 15 / 18
|  |  | 883 |  | 884 |  | 885 |  | 886 |  | 887 |  | 888 |  | 889 |  | 890 |  | 891 |  | 892 |  | 893 |  | 894 |  | 895 |  | 896 |  | 897 |  | 898 |  | 899 |  | 900 |  | 901 |  | 902 |  | 903 |  | 904 |  | 905 |  | 906 |  | 907 |  | 908 |  | 909 |  | 910 |  | 911 |  | 912 |  | 913 |  | 914 |  | 915 |  | 916 |  | 917 |  | 918 |  | 919 |  | 920 |  | 921 |  | 922 |  | 923 |  | 924 |  | 925 |  | 926 |  | 927 |  | 928 |  | 929 |  | 930 |  | 931 |  | 932 |  | 933 |  | 934 |  | 935 |  | 936 |  | 937 |  | 938 |  | 939 |  | 940 |  | 941 |  | 942 |  | 943 |  | 944 |  | 945
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading | [8 empty] | 29
|  | Stressing | [14 empty] | 29
|  | Grouting | [18 empty] | 29
| PL-2 | Threading | [10 empty] | 30
|  | Stressing | [16 empty] | 30
|  | Grouting | [20 empty] | 30
Basin B | PL-3 | Threading | [82 empty] | 21
|  | Stressing | [88 empty] | 21
|  | Grouting | [92 empty] | 21
| PL-4 | Threading | [84 empty] | 22
|  | Stressing | [90 empty] | 22
|  | Grouting | [94 empty] | 22
Basin C | PL-5 | Threading
Stressing
Grouting
| SPE | Threading
Stressing
Grouting
28/04/2029 → 29/06/2029 · page 16 / 18
|  |  | 946 |  | 947 |  | 948 |  | 949 |  | 950 |  | 951 |  | 952 |  | 953 |  | 954 |  | 955 |  | 956 |  | 957 |  | 958 |  | 959 |  | 960 |  | 961 |  | 962 |  | 963 |  | 964 |  | 965 |  | 966 |  | 967 |  | 968 |  | 969 |  | 970 |  | 971 |  | 972 |  | 973 |  | 974 |  | 975 |  | 976 |  | 977 |  | 978 |  | 979 |  | 980 |  | 981 |  | 982 |  | 983 |  | 984 |  | 985 |  | 986 |  | 987 |  | 988 |  | 989 |  | 990 |  | 991 |  | 992 |  | 993 |  | 994 |  | 995 |  | 996 |  | 997 |  | 998 |  | 999 |  | 1000 |  | 1001 |  | 1002 |  | 1003 |  | 1004 |  | 1005 |  | 1006 |  | 1007 |  | 1008
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
Stressing
Grouting
| PL-2 | Threading
Stressing
Grouting
Basin B | PL-3 | Threading | [96 empty] | 26
|  | Stressing | [102 empty] | 26
|  | Grouting | [106 empty] | 26
| PL-4 | Threading | [98 empty] | 27
|  | Stressing | [104 empty] | 27
|  | Grouting | [108 empty] | 27
Basin C | PL-5 | Threading | [16 empty] | 23
|  | Stressing | [22 empty] | 23
|  | Grouting | [26 empty] | 23
| SPE | Threading
Stressing
Grouting
30/06/2029 → 31/08/2029 · page 17 / 18
|  |  | 1009 |  | 1010 |  | 1011 |  | 1012 |  | 1013 |  | 1014 |  | 1015 |  | 1016 |  | 1017 |  | 1018 |  | 1019 |  | 1020 |  | 1021 |  | 1022 |  | 1023 |  | 1024 |  | 1025 |  | 1026 |  | 1027 |  | 1028 |  | 1029 |  | 1030 |  | 1031 |  | 1032 |  | 1033 |  | 1034 |  | 1035 |  | 1036 |  | 1037 |  | 1038 |  | 1039 |  | 1040 |  | 1041 |  | 1042 |  | 1043 |  | 1044 |  | 1045 |  | 1046 |  | 1047 |  | 1048 |  | 1049 |  | 1050 |  | 1051 |  | 1052 |  | 1053 |  | 1054 |  | 1055 |  | 1056 |  | 1057 |  | 1058 |  | 1059 |  | 1060 |  | 1061 |  | 1062 |  | 1063 |  | 1064 |  | 1065 |  | 1066 |  | 1067 |  | 1068 |  | 1069 |  | 1070 |  | 1071
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
Stressing
Grouting
| PL-2 | Threading
Stressing
Grouting
Basin B | PL-3 | Threading | [96 empty] | 31
|  | Stressing | [102 empty] | 31
|  | Grouting | [106 empty] | 31
| PL-4 | Threading | [98 empty] | 32
|  | Stressing | [104 empty] | 32
|  | Grouting | [108 empty] | 32
Basin C | PL-5 | Threading | [30 empty] | 28
|  | Stressing | [36 empty] | 28
|  | Grouting | [40 empty] | 28
| SPE | Threading
Stressing
Grouting
01/09/2029 → 22/09/2029 · page 18 / 18
|  |  | 1072 |  | 1073 |  | 1074 |  | 1075 |  | 1076 |  | 1077 |  | 1078 |  | 1079 |  | 1080 |  | 1081 |  | 1082 |  | 1083 |  | 1084 |  | 1085 |  | 1086 |  | 1087 |  | 1088 |  | 1089 |  | 1090 |  | 1091 |  | 1092 |  | 1093
|  |  | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N | D | N
Basin A | PL-1 | Threading
Stressing
Grouting
| PL-2 | Threading
Stressing
Grouting
Basin B | PL-3 | Threading
Stressing
Grouting
| PL-4 | Threading
Stressing
Grouting
Basin C | PL-5 | Threading | [30 empty] | 33
|  | Stressing | [36 empty] | 33
|  | Grouting | [40 empty] | 33
| SPE | Threading
Stressing
Grouting